## FastTracker2
Description | Estimated Hours | Actual Hours
Solution / Framework | 30 | 30
Update Assemblies | 10
Package Management | 10
Other | 10
User Interface | 30 | 25
Bootstrap | 15
Theme Set Up | 15
Model Design | 45 | 30
Org Models | 30
System Models | 15
Controllers | 40 | 20
Org Cotrollers | 25
System Controllers | 15
Views | 40 | 25
Org Views | 30
System Views | 10
Identity/Authorization | 40 | 30
Search Engine | 40 | 15
Install/Config | 15
Integration | 25
SSL Set Up | 15 | 0
Testing and Deployment | 50 | 0
Testing | 15
Bug Fixes | 20
Documentation | 15
Total Hours | 330 | 175
Rate | 120 | 120
Total Cost | 39600 | 21000